Annex 2:  ICR 2015-2018 HR Excellence in Research New Action Plan December 2016 - 2018

| 2014-2018 ICR Action plan |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Action | Owner(s) and related action plans | Success Measure |  |
| - Using data to inform priorities and measure impact |  |  |  |  |
| 1a | - Run Staff Survey triennially rather than annually - to be next rerun in May/June 2017 (new action) Concordat principle 7 | Head of OD | i) The survey will not be repeated until May 2017 to avoid survey fatigue. 2017 staff data to be analysed and compared to 2014 and 2015 (abridged) surveys to monitor trends in preparation for Athena SWAN reaccreditation/Gold in 2019. Will aim for an 80% completion rate |  |
| 1b | - Separate survey data out for research versus non-research staff, and further analysis for divisions and different staff groups (postdocs, team leaders and other research staff). Feed in to Athena SWAN groups, staff/student associations and benchmark to CROS/PIRLS. (follow on action) Concordat principle 7 | Head of OD, RDC, ASC | i) Divisional data provided to all team leaders – by December 2017. Discuss gender-related differences with divisional Athena SWAN reps and identify local issues to address and organisation issues to be raised at ASSSG by March 2018. ii)Analysis for research staff only, internal news article to publicise results – by February 2018 and used to inform Athena SWAN reaccreditation/Gold application in 2019 iii)Staff group data provided to staff associations – by Feb 2018 |  |
| 1c | - Improved recruitment data (follow on action) - Improve transparency of recruitment of team leaders/heads of division(follow on action) Concordat principles 1, 6 | HR Director HR IO Action plan: ASSSG | i)Once the e-recruitment software update has been purchased (delayed - est. March 2017), team leaders will be reminded to complete eRecruitment shortlist data by HR advisers for every recruitment campaign. We will aim for at least 50% of managers using the shortlisting module by March 2018 ii) A review of shortlisting processes in senior management recruitment will be undertaken by December 2017 and expanded to include all staff appointments once the new e-recruitment module is implemented and that data becomes available. |  |
| 1d | - Establish the career destinations of former researchers (postdocs, students, technical staff) (follow on action) Concordat principles 3, 4 | RDM, Head of Registry, RDC Action plan: HR Strategy RDC | i) Continue to curate the postdoc leaver’s data to maintain an accurate picture (>75% complete) of the next generation of leaders in the cancer research field, reporting on this biennially at the postdoc careers conference. ii)Continue to promote the LinkedIN online platform at postdoc events and include link in exit questionnaire for leavers to ensure there are always at least 100 members in the group. Report career destinations and impact biennially at the postdoc careers conference. iii) An initial analysis of SO next career destinations to be completed by Dec 2017 - aim to identify the next destinations of 60%. Findings to be presented to the SOA and at the annual SO conference. |  |
| 1e | i) Explore how to measure the impact of ICR-provided training/careers support on the careers of those who left ICR (follow on action) Concordat principles 3, 4 | RDA, RDC | i) Survey has been designed and will be piloted with the alumni members of the ICR postdoc LinkedIn group. Results of the survey will be reported to Athena SWAN Steering Committee by April 2017 including specific recommendations of support/best practice to help shape the ongoing training priorities for ICR researchers. |  |
| 1f | Evaluation of newly established cross organisational LGBT and BAME networks |  | Feedback will be requested from the ICR reps attending these networks to identify ways it can be improved and better publicised |  |
| 2) Leadership and management development |  |  |  |  |
| 2a | Mandatory equality and recruitment training: - Increase attendance of current staff on Equality Excellence training through improved monitoring at probation review point. (follow on action) - New recruitment training developed and offered to all panel chairs (follow on action) Concordat principles 1, 6 | Head of OD Action plan: ASSSG | i) 71% current staff have attended Equality training to date with the aim of increasing this to our original target of 80% by December 2017. ii) Recruitment training has been delivered to 46% panel chairs. Aim to reach our target of 60% of panel chairs by December 2017 following the implementation of the new e-recruitment system (with embedded training functionality) and subsequent promotion by HR (see action 1c). |  |
| 2b | Expand the portfolio of support provided to new team leaders via the established CDF network, providing bite-sized masterclasses on key skills (e.g. supervision skills) to build engagement of the group and involving senior faculty in delivering these. (follow on action) Concordat Principle 1, 2, 4, 5 | Head of OD, CDF network Action plan: ASSSG | i) Improved results in 2017 survey for team leader category against “I am given good training to perform in my current job” – aim to increase positive responses from 42% in 2014 to 55% in 2017 survey (not included in the abridged survey run in 2015). ii) Monitor progression of CDF to tenured faculty – aim to achieve 80% success for those reviews due in 2018/9. | i |
| 2c | Evaluation of the CDF/Faculty mentoring scheme that was set up in March 2015 (follow on action) Concordat Principle 1, 2, 4, 5 | Head of OD, Director of Academic Services | i) Mentors have now been provided for all CDF and best practice briefing offered, evaluation of the scheme will be completed by December 2016 to identify any improvements that can be made for CDFs going forward. |  |
| 2d | i)Increase awareness of the SO promotions criteria and associated mentoring scheme amongst all SO grades (new action) ii)Introduce a scientific officer award to raise the profile of SO grades and their contribution to ICR research Concordat Principle 2, 5, 6 | RDC RDC | i)Mentoring scheme to be promoted in iSpace articles timed with the promotions calls and SO grades to be surveyed at SO annual conference – aim for 70% to be aware of the scheme by September 2018 conference. ii)Team leaders will be asked to nominate a scientific officer who has made a valuable contribution to team working. Will aim for at least 6 nominations per year with the winner awarded by the chair of the annual ICR technical conference and communicated to all staff via internal newsletter |  |
| 2e | Supporting females aiming for or in leadership roles - Building on the evaluation of the Aurora and Future Leaders leadership programmes including we will track the long-term careers of alumni via LinkedIn (new action) - Ensure selection on to influential senior committees is transparent and fair (follow on action) - Aurora and future female leaders programme to be run in tandem from 2017 onwards (new action) - Evaluate the support provided to date for female team leaders (Women in Science Network) Concordat Principle 1, 2, 4, 5 | RDA, ASC, ASSSG Chair, ACS, Head of OD Action plan: ASSSG | i) Continue to monitor promotions/new career opportunities of attendees biennially, and review attendee feedback to ensure at least 80% of participants are highly satisfied with the programmes – aim to maintain the proportional increase in career success seen to date - report to Athena SWAN steering group. ii) Continue to ensure that committee places are advertised biannually & discussed as part of annual appraisal with those interested being encouraged to attend as observers initially. Aim to maintain or improve the current ratio of 44% of members of senior committees being female by December 2017. iii)At least 12 places to be offered on both programmes to corporate staff and researchers from 2017 onwards by an annual competitive application with ongoing evaluation and review iv)Evaluate recent cross organisational events aimed at female team leaders to identify priorities for the 2016/7 academic year and beyond. |  |
| 2f | Establish a new managers network (follow on action) Concordat principle 1, 2, 3, 4 | RDA, Head of OD | i) Places offered to all new managers in their first year of joining the ICR. Initial meeting to take place in Feb 2017. Feedback from attendees to be monitored after each session to ensure relevance and usefulness. We will monitor trends in the staff survey under category “My manager” from May 2017, tailoring future content accordingly. |  |
| 2g | Supporting postdocs aiming for leadership: i) Biennial running of Pathway to Independence, revised content based on feedback from pilot (follow on action) - Offer six places for Leadership in action in collaboration with UCL (follow on action) iii)Additional mentoring and careers support for postdoctoral fellowship holders (follow on action) Concordat principle 1, 2, 3 4, 5 | RDA, Academic Dean, Head of Organisational Development Action plan: ASSSG | i) Continued monitoring of feedback and careers of attendees (via dedicated LinkedIn group) to maintain at least 85% participants being highly satisifed. Develop content for June 2017 course in collaboration with key strategic partner institutions. ii) Continue running Leadership in Action run in collaboration with UCL and other London partners maintaining at least 80% satisfaction from postdoc and student participants. iii) Pilot mentoring event in Cancer Therapeutics with 21 students/postdocs and 5 team leaders to be evaluated by Jan 2017 before running a follow-up or trialling in other divisions and presenting to Athena SWAN silver group by Dec 2017. |  |
| 3) Defining career paths and supporting career development |  |  |  |  |
| 3a | Postdoc code of practice to be reviewed biennially and updated if necessary (new action) Concordat principle 2, 3, 4, 5 | RDA, HR Operations teams, HR IO, faculty | As code of practice is included in all contract packs, content and recommendations made in it should be reviewed by HR biennially to ensure correctness. |  |
| 3b | i) Ensure 70% of research staff are aware of access to impartial careers advice (follow on action) ii) To further raise awareness of researcher access to independent careers advice (new action) Concordat principle 2, 3 | RDA, RDC RDC/RDM | i) Achieve at least 70% positive response from researchers in 2017 survey following an increased emphasis on careers advice at 2015/6 researcher conferences. ii)Training brochure to be produced and circulated to all new starters of scientific officer grades and PDTF to promote career support and the work of the SOA/PDAC by January 2017 ii)Widespread advertising of opportunities to receive independent careers advice at postdoc careers conference (Jan 2017) and SO technical conference (Sept 2017) as well as through the bimonthly training bulletins sent to all staff. |  |
| 3c |  |  |  |  |
| 3c | i)Review of the clinical academic career development programme following the initial gap analysis on the career development available to clinical academics (new action) ii)Review the pilot Pathways to Independence for Clinicians first run in Nov 2016 (new action) Concordat principles 3,4 | RDA, ASSSG, CRCDWG Chair | i)Delegate feedback to be reviewed from all sessions run so far (Jan 2017), with the aim of shaping the ongoing clinical academic career development programme. ii)Review initial Clinician Pathways programme and aim for 80% delegates being highly satisfied with the course and tracking delegate career progression (by Nov 2017) in order to determine future running and relevant collaboration (biennially from Nov 2018 onwards) |  |
| 3d | Establish a mentoring scheme for clinical academics (follow on action) Concordat principles 4, 5, 6 | ASC, Deputy Director of BRC, Action plan: ASSSG. | Mentors identified and offered to 13 female clinical academics to date. Independent evaluation of scheme (highlighted as best practice case study by Vitae) due March 2017 which will shape how the scheme is rolled out to all clinical academics. |  |
| 3e | Develop and pilot an introduction to Bioinformatics programme (follow on action) Concordat principles 3, 4 | RDC | Whole bioinformatics support programme to be reviewed in January 2017 to determine ongoing support (Sept 2017 onwards) for those working in scientific computing. |  |
| 3f | Early training needs screening tool developed for students to complete during induction week.(follow on action) Concordat principles 4, 5 | Asst Dir (AR) Action plan: SSTR | 51% of initial cohort accessed the screening tool. From October 2016 students who have not logged in will be sent a follow up email to encourage them to do so. Completion rates for use of the tool will be reviewed annually. |  |
| 3g | Training in best practice for keeping laboratory records to be given to all new students (new action) Concordat principles 3 | RDC | Following requests from students for more guidance in this area, a session to be developed with the Academic Dean’s Team to be delivered at 2016 student induction and reviewed for inclusion at all inductions going forward |  |

Glossary

ASSSG – Athena SWAN Silver Steering Group

ACS – Assistant company secretary

ASC – Athena SWAN coordinator

BRC – Biomedical Research Centre

CRCDWG – Clinical Research Career Development Working Group

Head of OD – Head of Organisational Development

HoCS – Head of Clinical Studies

HR IO - HR Information Officer

HR OPS – HR Operations Manager

RDA/RDM – Researcher Development Advisor/Manager (Role name changed)

RDC – Researcher Development Coordinator

RDPEM – Research Degrees Programme and Events Manager

SCUF – Scientific Computer Users Forum

SO – Scientific Officer (technical staff)

SSTR – Strategic Student Training Review (Triennial)